## Dashboard
Metric | Value
Total Days | 180
Completed Days | 0
Completion % | 0%
Target Hours | 465
Actual Hours | 0
Projects / Capstones | 8
Current Streak | Track manually

## Daily Tracker
Day | Date | Phase | Track | Topic | Daily Task / Deliverable | Resource | YouTube Lecture | Status | Hours Planned | Hours Actual | Confidence (1-5) | Notes
1 | 2026-10-06 | Phase 1 — Coding Foundations | Python | Environment, VS Code, terminal, print, variables | Install Python/VS Code; write 5 tiny programs | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
2 | 2026-10-07 | Phase 1 — Coding Foundations | Python | Functions, arguments, return values | Solve 10 function exercises | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
3 | 2026-10-08 | Phase 1 — Coding Foundations | Python | Strings and formatting | Build a text formatter | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
4 | 2026-10-09 | Phase 1 — Coding Foundations | Python | Numbers, booleans, comparisons | Build calculator + unit converter | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
5 | 2026-10-10 | Phase 1 — Coding Foundations | Python | Conditionals | Build grade/eligibility checker | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
6 | 2026-10-11 | Phase 1 — Coding Foundations | Python | Loops: for/while | Solve 15 loop problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
7 | 2026-10-12 | Phase 1 — Coding Foundations | Python | Lists and tuples | Build list statistics program | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
8 | 2026-10-13 | Phase 1 — Coding Foundations | Python | Dictionaries and sets | Build frequency counter | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
9 | 2026-10-14 | Phase 1 — Coding Foundations | Python | Comprehensions | Rewrite 10 loops as comprehensions | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
10 | 2026-10-15 | Phase 1 — Coding Foundations | Python | Exceptions | Add validation/error handling to prior projects | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
11 | 2026-10-16 | Phase 1 — Coding Foundations | Python | Modules and packages | Split a project into modules | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
12 | 2026-10-17 | Phase 1 — Coding Foundations | Python | File I/O | Build CSV reader/writer | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
13 | 2026-10-18 | Phase 1 — Coding Foundations | Python | JSON | Build JSON config loader | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
14 | 2026-10-19 | Phase 1 — Coding Foundations | Python | Regular expressions | Extract emails/phone numbers from text | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
15 | 2026-10-20 | Phase 1 — Coding Foundations | Python | Classes and objects | Model Student/Course objects | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
16 | 2026-10-21 | Phase 1 — Coding Foundations | Python | OOP inheritance/composition | Refactor previous project with classes | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
17 | 2026-10-22 | Phase 1 — Coding Foundations | Python | Testing with pytest | Write tests for 3 functions | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
18 | 2026-10-23 | Phase 1 — Coding Foundations | Python | Debugging | Debug 5 intentionally broken programs | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
19 | 2026-10-24 | Phase 1 — Coding Foundations | Python | HTTP/API basics | Call a public API with Python | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
20 | 2026-10-25 | Phase 1 — Coding Foundations | Python | requests + API errors | Build weather/API CLI | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
21 | 2026-10-26 | Phase 1 — Coding Foundations | Python | Problem solving | 20 easy coding problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
22 | 2026-10-27 | Phase 1 — Coding Foundations | Python | Problem solving | 20 more problems; focus on patterns | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
23 | 2026-10-28 | Phase 1 — Coding Foundations | Python | Data structures | Implement stack, queue, hashmap basics | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
24 | 2026-10-29 | Phase 1 — Coding Foundations | Python | Algorithms | Implement binary search + sorting | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
25 | 2026-10-30 | Phase 1 — Coding Foundations | Git | Git init/add/commit/status/log | Create first Git repo | https://docs.github.com/en/get-started/learning-to-code/getting-started-with-git | https://www.youtube.com/watch?v=RGOj5yH7evk | Not Started | 2.5
26 | 2026-10-31 | Phase 1 — Coding Foundations | Git | Branches and merges | Practice 5 branch/merge scenarios | https://docs.github.com/en/get-started/learning-to-code/getting-started-with-git | https://www.youtube.com/watch?v=RGOj5yH7evk | Not Started | 2.5
27 | 2026-11-01 | Phase 1 — Coding Foundations | Git | GitHub | Push 2 projects; write README | https://docs.github.com/en/get-started/learning-to-code/getting-started-with-git | https://www.youtube.com/watch?v=RGOj5yH7evk | Not Started | 2.5
28 | 2026-11-02 | Phase 1 — Coding Foundations | Git | Pull requests/issues | Create issue + PR on your repo | https://docs.github.com/en/get-started/learning-to-code/getting-started-with-git | https://www.youtube.com/watch?v=RGOj5yH7evk | Not Started | 2.5
29 | 2026-11-03 | Phase 1 — Coding Foundations | Python | Mini-project planning | Design CLI expense tracker | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
30 | 2026-11-04 | Phase 1 — Coding Foundations | Python | Mini-project build | Finish + test + publish expense tracker | https://cs50.harvard.edu/python/ | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Not Started | 2.5
31 | 2026-11-05 | Phase 2 — CS + Software Engineering | CS | Big-O notation | Analyze 20 code snippets | https://cs50.harvard.edu/college/2026/fall/weeks/ |  | Not Started | 2.5
32 | 2026-11-06 | Phase 2 — CS + Software Engineering | DSA | Arrays/strings | 20 pattern problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
33 | 2026-11-07 | Phase 2 — CS + Software Engineering | DSA | Hashing | 15 hash-map/set problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
34 | 2026-11-08 | Phase 2 — CS + Software Engineering | DSA | Two pointers | 15 problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
35 | 2026-11-09 | Phase 2 — CS + Software Engineering | DSA | Sliding window | 15 problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
36 | 2026-11-10 | Phase 2 — CS + Software Engineering | DSA | Stack/queue | 15 problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
37 | 2026-11-11 | Phase 2 — CS + Software Engineering | DSA | Linked lists | 10 problems + implement list | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
38 | 2026-11-12 | Phase 2 — CS + Software Engineering | DSA | Trees/BST | 10 problems + traversal implementations | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
39 | 2026-11-13 | Phase 2 — CS + Software Engineering | DSA | Heaps | 10 problems + heap implementation | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
40 | 2026-11-14 | Phase 2 — CS + Software Engineering | DSA | Graphs | BFS/DFS + 10 problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
41 | 2026-11-15 | Phase 2 — CS + Software Engineering | DSA | Recursion/backtracking | 10 problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
42 | 2026-11-16 | Phase 2 — CS + Software Engineering | DSA | Sorting | Implement merge/quick sort; compare complexity | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
43 | 2026-11-17 | Phase 2 — CS + Software Engineering | DSA | Binary search | 10 problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
44 | 2026-11-18 | Phase 2 — CS + Software Engineering | DSA | Dynamic programming intro | 5 classic problems | https://cs50.harvard.edu/python/ | https://www.youtube.com/watch?v=8hly31xKli0 | Not Started | 2.5
45 | 2026-11-19 | Phase 2 — CS + Software Engineering | SQL | SELECT, WHERE, ORDER BY | Complete SQLBolt lessons 1–5 | https://sqlbolt.com/ | https://www.youtube.com/watch?v=HXV3zeQKqGY | Not Started | 2.5
46 | 2026-11-20 | Phase 2 — CS + Software Engineering | SQL | JOINs | Complete JOIN lessons | https://sqlbolt.com/ | https://www.youtube.com/watch?v=HXV3zeQKqGY | Not Started | 2.5
47 | 2026-11-21 | Phase 2 — CS + Software Engineering | SQL | Aggregations/GROUP BY | Complete aggregate lessons | https://sqlbolt.com/ | https://www.youtube.com/watch?v=HXV3zeQKqGY | Not Started | 2.5
48 | 2026-11-22 | Phase 2 — CS + Software Engineering | SQL | INSERT/UPDATE/DELETE | Complete CRUD lessons | https://sqlbolt.com/ | https://www.youtube.com/watch?v=HXV3zeQKqGY | Not Started | 2.5
49 | 2026-11-23 | Phase 2 — CS + Software Engineering | SQL | DDL/schema design | Create 3-table schema | https://sqlbolt.com/ | https://www.youtube.com/watch?v=HXV3zeQKqGY | Not Started | 2.5
50 | 2026-11-24 | Phase 2 — CS + Software Engineering | SQL | Subqueries/unions | Complete intermediate SQL topics | https://sqlbolt.com/ | https://www.youtube.com/watch?v=HXV3zeQKqGY | Not Started | 2.5
51 | 2026-11-25 | Phase 2 — CS + Software Engineering | SQL | Indexes/transactions | Learn concepts; write notes | https://sqlbolt.com/ | https://www.youtube.com/watch?v=HXV3zeQKqGY | Not Started | 2.5
52 | 2026-11-26 | Phase 2 — CS + Software Engineering | APIs | REST, JSON, HTTP status codes | Design 5 API endpoints | https://cs50.harvard.edu/python/ | https://www.youtube.com/@freecodecamp | Not Started | 2.5
53 | 2026-11-27 | Phase 2 — CS + Software Engineering | Backend | FastAPI basics | Build CRUD API | https://cs50.harvard.edu/python/ | https://www.youtube.com/@freecodecamp | Not Started | 2.5
54 | 2026-11-28 | Phase 2 — CS + Software Engineering | Engineering | Logging/config/env vars | Productionize CRUD API | https://madewithml.com/ | https://www.youtube.com/@MadeWithML | Not Started | 2.5
55 | 2026-11-29 | Phase 2 — CS + Software Engineering | Engineering | Testing API | Unit + integration tests | https://madewithml.com/ | https://www.youtube.com/@MadeWithML | Not Started | 2.5
56 | 2026-11-30 | Phase 3 — Math + Data | Engineering | Docker basics | Containerize API | https://madewithml.com/ | https://www.youtube.com/@MadeWithML | Not Started | 2.5
57 | 2026-12-01 | Phase 3 — Math + Data | Math | Vectors | Implement vector operations in NumPy | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
58 | 2026-12-02 | Phase 3 — Math + Data | Math | Matrices | Matrix multiplication + intuition | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
59 | 2026-12-03 | Phase 3 — Math + Data | Math | Dot product/cosine similarity | Build similarity calculator | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
60 | 2026-12-04 | Phase 3 — Math + Data | Math | Probability basics | Solve 20 probability questions | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
61 | 2026-12-05 | Phase 3 — Math + Data | Math | Distributions | Simulate normal/binomial distributions | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
62 | 2026-12-06 | Phase 3 — Math + Data | Math | Mean/variance/std | Implement from scratch + NumPy | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
63 | 2026-12-07 | Phase 3 — Math + Data | Math | Correlation/covariance | Analyze a small dataset | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
64 | 2026-12-08 | Phase 3 — Math + Data | Math | Derivatives | Understand slope/gradient visually | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
65 | 2026-12-09 | Phase 3 — Math + Data | Math | Gradient descent | Implement 1D gradient descent | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
66 | 2026-12-10 | Phase 3 — Math + Data | Math | Partial derivatives | Work through simple multivariable examples | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=T3TpdPmTLso | Not Started | 2.5
67 | 2026-12-11 | Phase 3 — Math + Data | NumPy | Arrays/indexing | Complete NumPy exercises | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=r-uOLxNrNk8 | Not Started | 2.5
68 | 2026-12-12 | Phase 3 — Math + Data | Pandas | DataFrames | Load/clean/analyze CSV | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=r-uOLxNrNk8 | Not Started | 2.5
69 | 2026-12-13 | Phase 3 — Math + Data | Pandas | Groupby/merge | Analyze dataset | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=r-uOLxNrNk8 | Not Started | 2.5
70 | 2026-12-14 | Phase 3 — Math + Data | Visualization | Matplotlib | Create 5 useful charts | https://www.deeplearning.ai/courses/ |  | Not Started | 2.5
71 | 2026-12-15 | Phase 3 — Math + Data | Data | Cleaning/missing values | Clean messy dataset | https://www.deeplearning.ai/courses/ |  | Not Started | 2.5
72 | 2026-12-16 | Phase 3 — Math + Data | Data | Train/test split | Practice with dataset | https://www.deeplearning.ai/specializations/machine-learning/ |  | Not Started | 2.5
73 | 2026-12-17 | Phase 3 — Math + Data | Data | Feature engineering | Create useful features | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/@MadeWithML | Not Started | 2.5
74 | 2026-12-18 | Phase 3 — Math + Data | Data | Evaluation metrics | Compare accuracy/precision/recall/F1 | https://www.deeplearning.ai/specializations/machine-learning/ |  | Not Started | 2.5
75 | 2026-12-19 | Phase 3 — Math + Data | Data | Data leakage/overfitting | Write checklist + examples | https://www.deeplearning.ai/specializations/machine-learning/ |  | Not Started | 2.5
76 | 2026-12-20 | Phase 4 — Machine Learning | Project | EDA project | Analyze a real dataset end-to-end | https://www.deeplearning.ai/courses/ |  | Not Started | 3.5
77 | 2026-12-21 | Phase 4 — Machine Learning | ML | ML workflow | Start Andrew Ng ML course | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
78 | 2026-12-22 | Phase 4 — Machine Learning | ML | Linear regression | Implement + use sklearn | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
79 | 2026-12-23 | Phase 4 — Machine Learning | ML | Gradient descent | Implement regression from scratch | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
80 | 2026-12-24 | Phase 4 — Machine Learning | ML | Multiple regression | Train/evaluate model | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
81 | 2026-12-25 | Phase 4 — Machine Learning | ML | Logistic regression | Build binary classifier | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
82 | 2026-12-26 | Phase 4 — Machine Learning | ML | Regularization | Compare L1/L2 | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
83 | 2026-12-27 | Phase 4 — Machine Learning | ML | Classification metrics | ROC-AUC, PR curve, confusion matrix | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
84 | 2026-12-28 | Phase 4 — Machine Learning | ML | Decision trees | Train and visualize | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
85 | 2026-12-29 | Phase 4 — Machine Learning | ML | Random forests | Compare with tree | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
86 | 2026-12-30 | Phase 4 — Machine Learning | ML | Boosting/XGBoost | Train boosted model | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
87 | 2026-12-31 | Phase 4 — Machine Learning | ML | Cross-validation | Implement evaluation pipeline | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
88 | 2027-01-01 | Phase 4 — Machine Learning | ML | Hyperparameter tuning | Grid/random search | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
89 | 2027-01-02 | Phase 4 — Machine Learning | ML | Feature scaling | Compare scaled/unscaled models | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
90 | 2027-01-03 | Phase 4 — Machine Learning | ML | Clustering | K-means project | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
91 | 2027-01-04 | Phase 4 — Machine Learning | ML | PCA | Dimensionality reduction experiment | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
92 | 2027-01-05 | Phase 4 — Machine Learning | ML | Anomaly detection | Build simple detector | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
93 | 2027-01-06 | Phase 4 — Machine Learning | ML | Recommenders | Understand collaborative filtering | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
94 | 2027-01-07 | Phase 4 — Machine Learning | ML | Model selection | Create model comparison table | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
95 | 2027-01-08 | Phase 4 — Machine Learning | ML | Explainability | Feature importance/SHAP concept | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
96 | 2027-01-09 | Phase 4 — Machine Learning | ML | Model persistence | Save/load model | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
97 | 2027-01-10 | Phase 4 — Machine Learning | Project | ML project | Build prediction/classification app | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 3.5
98 | 2027-01-11 | Phase 4 — Machine Learning | Project | ML API | Serve model through FastAPI | https://madewithml.com/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 3.5
99 | 2027-01-12 | Phase 4 — Machine Learning | Project | Docker ML | Containerize model API | https://madewithml.com/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 3.5
100 | 2027-01-13 | Phase 4 — Machine Learning | Project | Evaluation | Write model card + error analysis | https://madewithml.com/ |  | Not Started | 3.5
101 | 2027-01-14 | Phase 4 — Machine Learning | Project | Deploy | Deploy project to a cloud platform | https://madewithml.com/ |  | Not Started | 3.5
102 | 2027-01-15 | Phase 4 — Machine Learning | Review | ML revision | Explain 20 concepts without notes | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
103 | 2027-01-16 | Phase 4 — Machine Learning | Review | ML interview | Answer 30 ML questions | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
104 | 2027-01-17 | Phase 4 — Machine Learning | Review | ML debugging | Diagnose 5 bad models | https://www.deeplearning.ai/specializations/machine-learning/ | https://www.youtube.com/watch?v=jGwO_UgTS7I | Not Started | 2.5
105 | 2027-01-18 | Phase 4 — Machine Learning | Review | Portfolio | Document ML project | https://www.deeplearning.ai/specializations/machine-learning/ |  | Not Started | 2.5
106 | 2027-01-19 | Phase 5 — Deep Learning + PyTorch | DL | Neural network intuition | Learn neurons/activations | https://www.deeplearning.ai/specializations/deep-learning/ | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
107 | 2027-01-20 | Phase 5 — Deep Learning + PyTorch | DL | Perceptron | Implement simple perceptron | https://www.deeplearning.ai/specializations/deep-learning/ | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
108 | 2027-01-21 | Phase 5 — Deep Learning + PyTorch | DL | Forward propagation | Implement tiny network | https://www.deeplearning.ai/specializations/deep-learning/ | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
109 | 2027-01-22 | Phase 5 — Deep Learning + PyTorch | DL | Backpropagation | Derive intuition + code | https://www.deeplearning.ai/specializations/deep-learning/ | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
110 | 2027-01-23 | Phase 5 — Deep Learning + PyTorch | DL | Loss functions | Compare common losses | https://www.deeplearning.ai/specializations/deep-learning/ | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
111 | 2027-01-24 | Phase 5 — Deep Learning + PyTorch | DL | Optimizers | SGD/Adam intuition | https://www.deeplearning.ai/specializations/deep-learning/ | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
112 | 2027-01-25 | Phase 5 — Deep Learning + PyTorch | DL | PyTorch tensors | Complete PyTorch basics | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
113 | 2027-01-26 | Phase 5 — Deep Learning + PyTorch | PyTorch | Datasets/dataloaders | Build data pipeline | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate | https://www.youtube.com/watch?v=V_xro1bcAuA | Not Started | 2.5
114 | 2027-01-27 | Phase 5 — Deep Learning + PyTorch | PyTorch | Training loop | Write loop from scratch | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate | https://www.youtube.com/watch?v=V_xro1bcAuA | Not Started | 2.5
115 | 2027-01-28 | Phase 5 — Deep Learning + PyTorch | PyTorch | Validation/checkpoints | Add evaluation + saving | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate | https://www.youtube.com/watch?v=V_xro1bcAuA | Not Started | 2.5
116 | 2027-01-29 | Phase 5 — Deep Learning + PyTorch | DL | CNNs | Build image classifier | https://www.deeplearning.ai/specializations/deep-learning/ | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
117 | 2027-01-30 | Phase 5 — Deep Learning + PyTorch | DL | Transfer learning | Fine-tune pretrained vision model | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
118 | 2027-01-31 | Phase 5 — Deep Learning + PyTorch | DL | Embeddings | Understand learned representations | https://www.deeplearning.ai/specializations/deep-learning/ | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
119 | 2027-02-01 | Phase 5 — Deep Learning + PyTorch | NLP | Tokenization | Experiment with tokenization | https://huggingface.co/learn/llm-course/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
120 | 2027-02-02 | Phase 5 — Deep Learning + PyTorch | NLP | RNN/LSTM concepts | Understand historical sequence models | https://www.deeplearning.ai/specializations/deep-learning/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
121 | 2027-02-03 | Phase 5 — Deep Learning + PyTorch | NLP | Attention | Understand attention step-by-step | https://www.deeplearning.ai/specializations/deep-learning/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
122 | 2027-02-04 | Phase 5 — Deep Learning + PyTorch | NLP | Transformers | Learn encoder/decoder architecture | https://www.deeplearning.ai/specializations/deep-learning/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
123 | 2027-02-05 | Phase 5 — Deep Learning + PyTorch | NLP | Self-attention | Implement toy attention | https://www.deeplearning.ai/specializations/deep-learning/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
124 | 2027-02-06 | Phase 5 — Deep Learning + PyTorch | NLP | Fine-tuning | Fine-tune a pretrained model | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
125 | 2027-02-07 | Phase 5 — Deep Learning + PyTorch | Deployment | ONNX/optimization | Learn quantization/pruning concepts | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate | https://www.youtube.com/@MadeWithML | Not Started | 2.5
126 | 2027-02-08 | Phase 5 — Deep Learning + PyTorch | Project | Vision project | Train/fine-tune image model | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate |  | Not Started | 3.5
127 | 2027-02-09 | Phase 5 — Deep Learning + PyTorch | Project | NLP project | Text classification with pretrained model | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 3.5
128 | 2027-02-10 | Phase 5 — Deep Learning + PyTorch | Review | Deep learning revision | Explain backprop/attention/transformers | https://www.deeplearning.ai/specializations/deep-learning/ |  | Not Started | 2.5
129 | 2027-02-11 | Phase 5 — Deep Learning + PyTorch | Portfolio | DL writeup | Document experiments and results | https://www.deeplearning.ai/specializations/deep-learning/ | https://www.youtube.com/watch?v=CS4cs9xVecg | Not Started | 2.5
130 | 2027-02-12 | Phase 5 — Deep Learning + PyTorch | LLM | Tokens/context windows | Explain tokens and context | https://huggingface.co/learn/llm-course/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
131 | 2027-02-13 | Phase 5 — Deep Learning + PyTorch | LLM | Embeddings | Build semantic similarity demo | https://huggingface.co/learn/llm-course/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
132 | 2027-02-14 | Phase 5 — Deep Learning + PyTorch | LLM | Transformers | Read HF transformer workflow | https://huggingface.co/learn/llm-course/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
133 | 2027-02-15 | Phase 5 — Deep Learning + PyTorch | LLM | Prompting | Build prompt test set | https://www.deeplearning.ai/courses/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
134 | 2027-02-16 | Phase 5 — Deep Learning + PyTorch | LLM | Structured outputs | Build JSON-output application | https://www.deeplearning.ai/courses/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
135 | 2027-02-17 | Phase 5 — Deep Learning + PyTorch | LLM | Function/tool calling | Connect LLM to calculator/API | https://www.deeplearning.ai/courses/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
136 | 2027-02-18 | Phase 6 — LLM Engineering | LLM | RAG architecture | Draw and explain RAG | https://huggingface.co/learn/llm-course/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
137 | 2027-02-19 | Phase 6 — LLM Engineering | RAG | Chunking | Test 3 chunking strategies | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 2.5
138 | 2027-02-20 | Phase 6 — LLM Engineering | RAG | Embeddings + vector search | Build semantic search | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 2.5
139 | 2027-02-21 | Phase 6 — LLM Engineering | RAG | Retriever evaluation | Measure retrieval quality | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 2.5
140 | 2027-02-22 | Phase 6 — LLM Engineering | RAG | Reranking | Understand rerankers | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 2.5
141 | 2027-02-23 | Phase 6 — LLM Engineering | RAG | Grounding/citations | Build cited RAG app | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 2.5
142 | 2027-02-24 | Phase 6 — LLM Engineering | RAG | PDF ingestion | Build PDF Q&A | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 2.5
143 | 2027-02-25 | Phase 6 — LLM Engineering | RAG | Hybrid search | Combine keyword + semantic search | https://madewithml.com/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 2.5
144 | 2027-02-26 | Phase 6 — LLM Engineering | LLM | Hallucinations | Create failure test set | https://huggingface.co/learn/llm-course/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
145 | 2027-02-27 | Phase 6 — LLM Engineering | LLM | Evaluation | Build 20-question eval dataset | https://www.deeplearning.ai/courses/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
146 | 2027-02-28 | Phase 6 — LLM Engineering | LLM | Latency/cost | Measure token usage and latency | https://www.deeplearning.ai/courses/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
147 | 2027-03-01 | Phase 6 — LLM Engineering | LLM | Guardrails | Add input/output validation | https://www.deeplearning.ai/courses/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
148 | 2027-03-02 | Phase 6 — LLM Engineering | LLM | Fine-tuning vs RAG | Decision framework | https://huggingface.co/learn/llm-course/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
149 | 2027-03-03 | Phase 6 — LLM Engineering | Project | RAG v1 | Build document assistant | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 3.5
150 | 2027-03-04 | Phase 6 — LLM Engineering | Project | RAG v2 | Add citations/evaluation | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 3.5
151 | 2027-03-05 | Phase 6 — LLM Engineering | Project | RAG v3 | Deploy and document | https://madewithml.com/ | https://www.youtube.com/watch?v=QZc7a0y2x4E | Not Started | 3.5
152 | 2027-03-06 | Phase 6 — LLM Engineering | Review | LLM interview | Answer 30 LLM questions | https://huggingface.co/learn/llm-course/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
153 | 2027-03-07 | Phase 6 — LLM Engineering | Portfolio | LLM writeup | Publish architecture + lessons | https://huggingface.co/learn/llm-course/ | https://huggingface.co/learn/llm-course/chapter1/1 | Not Started | 2.5
154 | 2027-03-08 | Phase 6 — LLM Engineering | Agents | Agent loop | Understand observe/think/act | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=Vv8JQx7Jp6Q | Not Started | 2.5
155 | 2027-03-09 | Phase 6 — LLM Engineering | Agents | Tool registry | Build 3 tools | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=Vv8JQx7Jp6Q | Not Started | 2.5
156 | 2027-03-10 | Phase 6 — LLM Engineering | Agents | Memory | Add short/long-term memory concept | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=Vv8JQx7Jp6Q | Not Started | 2.5
157 | 2027-03-11 | Phase 6 — LLM Engineering | Agents | Planning | Build multi-step workflow | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=Vv8JQx7Jp6Q | Not Started | 2.5
158 | 2027-03-12 | Phase 6 — LLM Engineering | Agents | Multi-agent | Experiment with specialist agents | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=Vv8JQx7Jp6Q | Not Started | 2.5
159 | 2027-03-13 | Phase 6 — LLM Engineering | Agents | Human-in-loop | Add approval step | https://www.deeplearning.ai/courses/ | https://www.youtube.com/watch?v=Vv8JQx7Jp6Q | Not Started | 2.5
160 | 2027-03-14 | Phase 6 — LLM Engineering | Agents | Reliability | Retries/timeouts/fallbacks | https://madewithml.com/ | https://www.youtube.com/watch?v=Vv8JQx7Jp6Q | Not Started | 2.5
161 | 2027-03-15 | Phase 7 — Production AI + Agents | MLOps | Tracing/observability | Log model/tool calls | https://madewithml.com/ | https://www.youtube.com/@MadeWithML | Not Started | 2.5
162 | 2027-03-16 | Phase 7 — Production AI + Agents | MLOps | Evaluation in CI | Run evals before deployment | https://madewithml.com/ | https://www.youtube.com/@MadeWithML | Not Started | 2.5
163 | 2027-03-17 | Phase 7 — Production AI + Agents | MLOps | Security | Prompt injection/data leakage basics | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/@MadeWithML | Not Started | 2.5
164 | 2027-03-18 | Phase 7 — Production AI + Agents | MLOps | Scaling | Caching/queues/rate limits | https://madewithml.com/ | https://www.youtube.com/@MadeWithML | Not Started | 2.5
165 | 2027-03-19 | Phase 7 — Production AI + Agents | Project | AI agent | Build research/automation agent | https://www.deeplearning.ai/courses/ |  | Not Started | 3.5
166 | 2027-03-20 | Phase 7 — Production AI + Agents | Project | Agent evaluation | Create task benchmark | https://madewithml.com/ |  | Not Started | 3.5
167 | 2027-03-21 | Phase 7 — Production AI + Agents | Project | Productionize | Docker + logging + tests | https://madewithml.com/ |  | Not Started | 3.5
168 | 2027-03-22 | Phase 7 — Production AI + Agents | Project | Deploy | Deploy AI agent | https://madewithml.com/ |  | Not Started | 3.5
169 | 2027-03-23 | Phase 7 — Production AI + Agents | Career | Portfolio audit | Select 3 strongest projects | https://madewithml.com/ | https://www.youtube.com/@ByteByteGo | Not Started | 2.5
170 | 2027-03-24 | Phase 7 — Production AI + Agents | Career | Resume/GitHub | Rewrite around AI engineering outcomes | https://docs.github.com/en/get-started/learning-to-code/getting-started-with-git | https://www.youtube.com/@ByteByteGo | Not Started | 2.5
171 | 2027-03-25 | Phase 7 — Production AI + Agents | Career | System design | Design an AI system end-to-end | https://madewithml.com/ | https://www.youtube.com/@ByteByteGo | Not Started | 2.5
172 | 2027-03-26 | Phase 7 — Production AI + Agents | Career | Interview | Mock AI/ML/LLM interview | https://huggingface.co/learn/llm-course/ | https://www.youtube.com/@ByteByteGo | Not Started | 2.5
173 | 2027-03-27 | Phase 7 — Production AI + Agents | Career | Capstone | Present final project + roadmap | https://www.deeplearning.ai/courses/ | https://www.youtube.com/@ByteByteGo | Not Started | 2.5
174 | 2027-03-28 | Phase 7 — Production AI + Agents | Review | Catch-up + spaced revision + portfolio maintenance | Complete missed work; revise weak areas | https://www.deeplearning.ai/courses/ |  | Not Started | 2.5
175 | 2027-03-29 | Phase 7 — Production AI + Agents | Review | Catch-up + spaced revision + portfolio maintenance | Complete missed work; revise weak areas | https://www.deeplearning.ai/courses/ |  | Not Started | 2.5
176 | 2027-03-30 | Phase 8 — Portfolio + Interview | Review | Catch-up + spaced revision + portfolio maintenance | Complete missed work; revise weak areas | https://www.deeplearning.ai/courses/ |  | Not Started | 2.5
177 | 2027-03-31 | Phase 8 — Portfolio + Interview | Review | Catch-up + spaced revision + portfolio maintenance | Complete missed work; revise weak areas | https://www.deeplearning.ai/courses/ |  | Not Started | 2.5
178 | 2027-04-01 | Phase 8 — Portfolio + Interview | Review | Catch-up + spaced revision + portfolio maintenance | Complete missed work; revise weak areas | https://www.deeplearning.ai/courses/ |  | Not Started | 2.5
179 | 2027-04-02 | Phase 8 — Portfolio + Interview | Review | Catch-up + spaced revision + portfolio maintenance | Complete missed work; revise weak areas | https://www.deeplearning.ai/courses/ |  | Not Started | 2.5
180 | 2027-04-03 | Phase 8 — Portfolio + Interview | Review | Catch-up + spaced revision + portfolio maintenance | Complete missed work; revise weak areas | https://www.deeplearning.ai/courses/ |  | Not Started | 2.5

## Roadmap
Phase | Days | Focus | Exit Criteria
Phase 1 — Coding Foundations | 30 | Python + Git + programming thinking | Can build/test/debug Python programs independently
Phase 2 — CS + Software Engineering | 25 | DSA + SQL + APIs + backend + Docker | Can reason about complexity, data, APIs and services
Phase 3 — Math + Data | 20 | Linear algebra + probability + NumPy/Pandas | Can manipulate data and explain core ML math
Phase 4 — Machine Learning | 30 | Classical ML + evaluation + deployment | Can train, evaluate and deploy classical ML models
Phase 5 — Deep Learning + PyTorch | 30 | Deep learning + PyTorch + Transformers | Can build/train/fine-tune DL models with PyTorch
Phase 6 — LLM Engineering | 25 | LLMs + embeddings + RAG + evaluation | Can build reliable RAG/LLM applications
Phase 7 — Production AI + Agents | 15 | Agents + MLOps + production AI | Can build and operate tool-using AI systems
Phase 8 — Portfolio + Interview | 5 | Portfolio + interview readiness | 3 strong projects + resume + interview readiness

## Resources
Resource | URL
Python | https://cs50.harvard.edu/python/
Git | https://docs.github.com/en/get-started/learning-to-code/getting-started-with-git
SQL | https://sqlbolt.com/
ML | https://www.deeplearning.ai/specializations/machine-learning/
DL | https://www.deeplearning.ai/specializations/deep-learning/
PyTorch | https://www.deeplearning.ai/specializations/pytorch-for-deep-learning-professional-certificate
HF | https://huggingface.co/learn/llm-course/
MadeWithML | https://madewithml.com/
DLAI | https://www.deeplearning.ai/courses/

## YouTube Resources
Phase | Track | YouTube Lecture / Playlist | Link | How to Use
Phase 1 | Python | CS50P — Lecture 0: Functions, Variables | https://www.youtube.com/watch?v=JP7ITIXGpHk | Use for Days 1–5; continue with the official CS50P lecture sequence.
Phase 1 | Python | CS50P — Official YouTube playlist | https://www.youtube.com/playlist?list=PLhQjrBD2T3817j24-GogXmWqO5Q5vYy0V | Primary lecture series for Python fundamentals.
Phase 2 | SQL | SQL and Databases — Full Course for Beginners | https://www.youtube.com/watch?v=HXV3zeQKqGY | Use for SQL/database fundamentals alongside SQLBolt.
Phase 2 | DSA | freeCodeCamp — Data Structures & Algorithms | https://www.youtube.com/watch?v=8hly31xKli0 | Use selectively for DSA concepts; solve problems after each topic.
Phase 2 | Git | Git & GitHub for Beginners | https://www.youtube.com/watch?v=RGOj5yH7evk | Use for Git/GitHub workflow.
Phase 3 | Math | Mathematics for Machine Learning — Full Course | https://www.youtube.com/watch?v=T3TpdPmTLso | Use selectively for vectors, matrices, probability and calculus.
Phase 3 | NumPy/Pandas | Data Analysis with Python — Full Course | https://www.youtube.com/watch?v=r-uOLxNrNk8 | Use for NumPy, Pandas and practical data analysis.
Phase 4 | Machine Learning | Stanford CS229 — Machine Learning Lecture 1 | https://www.youtube.com/watch?v=jGwO_UgTS7I | Deep conceptual ML lectures; use after the beginner ML course.
Phase 4 | Machine Learning | Andrew Ng — Machine Learning playlist | https://www.youtube.com/playlist?list=PLLssT5z_DsK-h9vYZkQkYNWcItqhlRJLN | Supplementary ML lecture series.
Phase 5 | Deep Learning | Deep Learning — Neural Networks / Andrew Ng | https://www.youtube.com/watch?v=CS4cs9xVecg | Conceptual introduction before/alongside the Deep Learning Specialization.
Phase 5 | PyTorch | PyTorch for Deep Learning — Full Course | https://www.youtube.com/watch?v=V_xro1bcAuA | Practical PyTorch; use for tensors, datasets, training and projects.
Phase 5 | Transformers | Hugging Face — Transformers Course | https://huggingface.co/learn/llm-course/chapter1/1 | Use as the main structured resource for Transformers.
Phase 6 | LLMs | Hugging Face LLM Course | https://www.youtube.com/playlist?list=PLo2EIpI_JMQv4RaU-0XQ8e9vT7rY1K6fD | Supplementary video learning; official course material is the source of truth.
Phase 6 | RAG | Complete RAG Tutorial 2026 — from Scratch | https://www.youtube.com/watch?v=QZc7a0y2x4E | Use for the RAG phase; pair with implementation and evaluation.
Phase 6 | LLM Engineering | DeepLearning.AI — LLM / Generative AI courses | https://www.youtube.com/@Deeplearningai | Use for short practical lectures on prompting, RAG, agents and evaluation.
Phase 7 | Agents | AI Agents Crash Course — Agentic & Multi-Agent Design Patterns | https://www.youtube.com/watch?v=Vv8JQx7Jp6Q | Use for agent loops, tools and multi-agent patterns.
Phase 7 | AI Engineering | Made With ML — AI/ML Engineering | https://www.youtube.com/@MadeWithML | Use for production, testing, evaluation, deployment and MLOps.
Phase 8 | Career | AI Engineering / System Design practice | https://www.youtube.com/@ByteByteGo | Use selectively for system design and architecture thinking.